## Sheet1
Date | Question/Issue Description | Originator | Answer/Notes | Contact | Status | Updates
2015-06-18 | Why can't you merge from parent to child workspace? | Brittany/Greg | You actually can. The selector tool is not obvious. Need to click on the Sub-branch. Need to click on the pencil icon next to the Branch Name to change the To/From branch. |  | Complete
2015-06-18 | Can you see the model hierarchy in EMS web app? | Brittany/Greg | Not right now. Part of C3 release later this year 3Q2015. |  | Complete
2015-07-10 | Per the user manual, it mentions that you have to perform the merge twice (once on EMS and another time on teamwork server). We see this as a potential problem and wonder if you have a best practice or a roadmap where you wouldn’t have to do the merge twice. Why not just allow model branches on EMS and get rid of teamwork server? | Brittany/Greg |  |  | Complete
2015-07-10 | In magic draw, there is the baseline tag on the ModelManagementSystem stereotype. This tag doesn’t seem to do anything..can you explain the purpose? We thought that maybe you could use that stereotype to indicate MD branches and not have to use teamwork server..but that doesn’t seem to be the case. |  | Ignore, this will be removed. |  | Complete
2015-06-18 | Why does Update not work from Magic Draw? | Brittany/Greg | There are patches available that would address this. Out by Monday next week. 6/22/15 |  | In Work
2015-06-18 | Alfresco Roles don't match the roles for v.4.2.4 but match the alfresco roles in v4.1. this seems wrong since we are using v4.2.4. what are the definitions of the roles? | Brittany/Greg | Would like Role definitions and permissions they have since different then published from 4.1. JPL will look into it. | cin young | In Work
2015-07-24 | How do you do branching/merging | Brittany/Greg |  |  | In Work
2015-07-24 | How do you do branching/merging with teamwork sever and Alfresco? | Brittany/Greg |  |  | In Work
| Write up SysML issue and submit | All | Added as an agenda item for 7/2 and invited Sandy |  | In Work
2015-07-30 | Change Management – Branching/Merging: a. Why are you using teamwork server? | Brittany | JPL is using teamwork server because not all information is stored in MMS. In the interim teamwork server will be required until MMS (load partial models and/or the entire model) is completed. This task to be completed by end of 2016. |  | In Work
2015-07-30 | How are you running your advanced queries within Open MBEE? | Brittany | Still in development, far now just on the MD side with options. database queries has early version, will require coding at this time (in development); integration code with mathematical (Chris will demo). | Chris Delp | In Work
2015-07-30 | What is the best way to load a large model? (e.g. xml data). | Greg | REST API. V2.2; will have M2 layer (MetaModelica/SysML). The View editor code/EMS repo test has examples. Chris Delp will provide project repo documentation (project wiki). | Chris Delp | In Work
2015-07-10 | Why are you using teamwork server? | Brittany/Greg | Refer to question (Change Management – Branching/Merging: a. Why are you using teamwork server?). |  | Redundant Question.
2015-07-30 | Change Management – Branching/Merging: b. Per the user manual, it mentions that you have to perform the merge twice (once on EMS and another time on teamwork server). We see this as a potential problem and wonder if you have a best practice or a roadmap where you wouldn’t have to do the merge twice. Why not just allow model branches on EMS and get rid of teamwork server? | Brittany | some data is not stored on MMS and vice-versa. Refer to question (Change Management – Branching/Merging: a. Why are you using teamwork server?) |  | Redundant Question.
2015-07-30 | Change Management – Branching/Merging: c. We noticed that you couldn’t see the model history or revert to prior models via EMS (or at least it isn’t mentioned in the user manual). Is there a way of doing this in EMS or is that something you have to do in the teamwork server? | Brittany | Refer to the following questions (How does a user revert data to a prior version?) & (We noticed that you couldn’t see the model history or revert to prior models via EMS (or at least it isn’t mentioned in the user manual). Is there a way of doing this in EMS?). |  | Redundant Question.
2015-07-24 | Query Engine | Brittany/Greg | Refer to question (How are you running your advanced queries within Open MBEE?). |  | Redundant Question.
2015-07-30 | Review github issue 17 | Brittany |  |  | Review
2015-07-30 | Review github issue 18 | Brittany |  |  | Review
2015-07-30 | Document Generation: c. Within MagicDraw the DocGen -> Generate Document menu pick does not generate an XML file. (there isn’t a github issue related to this problem, but Greg E is familiar with the problem). | Brittany/Greg | When generating "DocGen 3" error messages/warning are displayed that do not appear to be correct. Furthermore, the errors/warning should not impact the XML file from being generated. Chris Delp request that we send the data file to JPL for evaluation. | Chris Delp | Send data file to JPL
2015-06-19 | How does a user revert data to a prior version? | Brittany/Greg | Perform merge diff (specify a tag/different branch). Compare and pull change in. Note: v2.2 in-work for the following projects: share, SysML, ems repo, web app, util, bae, doc gen; source pushed but no builds. |  | Verify
2015-07-10 | We noticed that you couldn’t see the model history or revert to prior models via EMS (or at least it isn’t mentioned in the user manual). Is there a way of doing this in EMS? | Brittany/Greg | Make a tag for the area to examine. Edit the time stamp on the tag in order to move. Note: can't edit on web client. |  | Verify
2015-07-30 | Document Generation: a. How do you generate a document within EMS? (github issue #14) | Brittany/Greg | Make a tag from document; see menu option; generate PDF. In addition, JPL (Chris Delp) to send instructions. | Chris Delp | Verify
2015-07-30 | Document Generation: b. How do you generate a document from within Magic Draw? | Brittany/Greg | MD local generation. Greg E to investigate. |  | Verify